## WBS
Work Breakdown Structure
© 2017 by Vertex42.com
| Project Start | 01 Desember 2025 |  | Smart Transportation: Optimasi Rute Angkutan Umum |  |  | Work Breakdown Structure
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Phase 1 : Perencanaan | Project Manager | 2025-12-01 | 2025-12-14 | Kick-off, ruang lingkup | ◄ A Conditional Formatting rule formats Level 1 tasks
2 | 1.1 | Analisis Kebutuhan Sistem | Analis Sistem | 2025-12-01 | 2025-12-08 | Kumpulkan kebutuhan
3 | 1.1.1 | Identifikasi pengguna & stakeholder | Analis Sistem | 2025-12-01 | 2025-12-05 | Dishub, operator, penumpang
3 | 1.1.2 | Studi kelayakan proyek | Project Manager | 2025-12-06 | 2025-12-10 | Studi teknis, ekonomis, operasional, jadwal
3 | 1.2 | Penyusunan Dokumen Perencanaan | Project Manager | 2025-12-11 | 2025-12-14 | Dokumen lengkap, SRS awal
1 | 2 | Phase 2 : Desain Sistem | Tim Desain | 2025-12-15 | 2026-01-04
2 | 2.1 | Desain Arsitektur Smart Transportation | System Architect | 2025-12-15 | 2025-12-21 | Sensor, IoT, server pusat
2 | 2.2 | Desain Database Lalu Lintas | DBA | 2025-12-22 | 2025-12-28 | Data kendaraan, rute, sensor
2 | 2.3 | Desain UI Dashboard Monitoring | UI/UX Designer | 2025-12-29 | 2026-01-01 | Dashboard operator & admin
2 | 2.4 | Desain Aplikasi Mobile Pengguna | UI/UX Designer | 2026-01-02 | 2026-01-04 | Tracking bus, estimasi waktu
1 | 3 | Phase 3: Implementasi & Pengembangan | Tim Developer | 2026-01-05 | 2026-02-16
2 | 3.1 | Pengembangan Backend Sistem | Backend Dev | 2026-01-05 | 2026-01-18 | API GPS, rute, database
2 | 3.2 | Pengembangan Frontend Sistem | Frontend Dev | 2026-01-12 | 2026-01-25 | Web dashboard & UI
2 | 3.3 | Integrasi Database & API | Fullstack Dev | 2026-01-19 | 2026-02-02 | Koneksi database – backend
2 | 3.4 | Pengembangan Modul AI | AI Engineer | 2026-01-26 | 2026-02-16 | Algoritma optimasi rute
3 | 3.4.1 | Model prediksi kemacetan | AI Engineer | 2026-02-26 | 06/02/202 | Model pertama
3 | 3.4.2 | Model optimasi rute | AI Engineer | 2026-02-07 | 2026-02-13 | Rekomendasi rute
3 | 3.4.3 | Integrasi model ke API | Fullstack Dev | 2026-02-14 | 2026-02-16 | AI ke sistem real-time
1 | 4 | Phase 4 : Uji Coba & Implementasi | QA Tester | 2026-02-17 | 2026-03-07
2 | 4.1 | Pengujian Sistem (Unit & Integrasi) | QA Tester | 2026-02-17 | 2026-02-23 | Tes modul backend, AI, mobile
2 | 4.2 | Pengujian Sensor Lapangan | IoT Technician | 2025-02-24 | 2026-02-28 | Uji koneksi & akurasi data
2 | 4.3 | Pilot Testing di Area Tertentu | Project Manager | 2026-03-01 | 2026-03-04 | Implementasi skala kecil
2 | 4.4 | Go-Live Sistem Smart Transportation | Project Manager | 2026-03-05 | 2026-03-07 | Peluncuran resmi
1 | 5 | Phase 5 : Pemeliharaan & Evaluasi | IT Support | 2026-03-08 | 2026-04-05 | Monitoring berkala
2 | 5.1 | Monitoring Performa Sistem | IT Support | 2026-03-08 | 2026-04-06 | Cek bug & update ringan | ◄ Add new rows ABOVE this one.
2 | 5.2 | Evaluasi Kinerja AI & Rekomendasi Rute | Project Manager | 2026-03-14 | 2026-03-21 | Penilaian akurasi AI
2 | 5.3 | Pengembangan Fitur Lanjutan | Tim Developer | 2026-03-22 | 2026-04-05 | Penambahan fitur sesuai kebutuhan

## Help (hidden)
HELP
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html |  | © 2017 Vertex42 LLC
About this Template
This template provides a very basic WBS table that you can use for defining a hierarchical work breakdown structure for a project plan or process.
Want more features and automation?
Try the Gantt Chart Template by Vertex42.com
Note: The formula for the WBS numbering was developed by Vertex42.com for the Gantt Chart Template Pro spreadsheet, and is copyrighted. See the terms of use.
Instructions
1) | Choose a Level from the drop-down list in column B. The WBS code is created automatically. When adding rows, you will need to copy the formula in the WBS code column into the newly added rows.
2) | Indent Task Descriptions using the Indent buttons in the Home tab.
3) | Add or hide columns as needed.
4) | A conditional formatting rule automatically highlights level 1 tasks. Go to Home > Conditional Formatting > Manage Rules to remove or edit this rule.
Terms of Use
See the following page for information about how you may use this spreadsheet.
https://www.vertex42.com/licensing/EULA_privateuse.html
REFERENCES
SEE ALSO | Vertex42.com: Gantt Chart Template
SEE ALSO | Vertex42.com: Project Management Templates
TIPS | Vertex42.com: Spreadsheet Tips Workbook

## ©
Work Breakdown Structure
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.